## Sheet1
Section | Concern | Tester | Status | Priority | Developer | Screenshot or Video | Comment
Home>Featured | Featured section third product box does not have similar size than the rest of the product box. Third product box has to be similar size with the rest of the box. | Nolak | Will do | Low | Dev 1 | Bug1
Home | In top slider first iphone image doesn't load iphone display page when the image is clicked and second laptop image does not load anything when the image is clicked. In top slider both Iphone and laptop image should view their display page when those images are clicked. | Nolak | Will do | Medium | Dev 2 | Bug 2
Home>Featured | Featured section last two product's add to cart option loads product display page. Add to cart option of the last two product should load add to cart page. | Nolak | Will do | Medium | Dev 1 | Bug 3
Header and Footer | Phone number given in the header is not valid. Valid phone number should be given in the header. | Nolak | Will do | Medium | Dev 2 | Bug 4
Search | In logged in state, when valid product name was given in search box and search result shows 500-Internal Server Error. In logged in state,search box should accept the information and should display a page with exact products and similar products list. | Nolak | Blocker | High | Dev 1 | Bug 5
Search | In logged in state,when invalid product name was given in search box and search result shows 500-Internal Server Error. In logged in state, search result should show error message after taking invalid values. | Nolak | Blocker | High | Dev 1 | Bug 6
Search | Without logging in when product name was given in search box it shows 500-Internal Server Error. Search box should give a proper search result if the user is not logged in his id. | Nolak | Blocker | High | Dev 1 | Bug 7
Register | After registration confirmation mail is not sent to the registered email. Confirmation mail should be sent to the registered e-mail after registration. | Nolak | Will do | Medium | Dev 1 | Bug 8
Forgot Password | No reset pssword email has sent to the user for password reset. Reset password email should be sent to the user. | Nolak | Will do | High | Dev 2 | Bug 9
Forgot Password | Password can not be reset as no confirmation email with a new password link is sent. Should be able to reset password after getting the email with the reset password link. | Nolak | Blocker | High | Dev 2 | Bug 10
Forgot Password | User can not login after resetting password as no confirmation email with the reset password link has sent to the user for password reset. User should be able to login with the reset password. | Nolak | Blocker | High | Dev 2 | Bug 11
Edit Account | First Name and Last name field accepts small letters. First Name should accept only names that start with capital letter where rest of the letters are small and also accepts special character (.) and last name accepts only surnames that start with capital letter where rest of the letters are small and accept special characters(- ,') and space in between surname. | Nolak | Future release | Low | Dev 2 | Bug 12
Edit Account | First Name and Last name field accepts integers and special characters. First Name and Last name field should not accept names which have integers and special characters except hyphen,fullstop,apostrophe s. | Nolak | Will do | Low | Dev 2 | Bug 13
Edit Account | First Name and Last name field accept letters where every letter has space in between them. First Name and Last Name should not accept names which have spaces after each letter | Nolak | Future release | Low | Dev 2 | Bug 14
Edit Account | Error messege does not show when Continue button is clicked after accepting invalid email in email address field. Should show error messge when invalid email is used. | Nolak | Future release | Medium | Dev 2 | Bug 15
Change Password | Password field accepts 21 characters. Password field should accept characters between 4 to 20 and should be able to show an error message "Password must be between 4 and 20 characters!" under Password field. | Nolak | Will do | Medium | Dev 1 | Bug 16
Address Book | the Address Book page loads My Account page under Address Book entries after deleting an address. After deleting an address, Address Book should show only Address Book page with a success message "Your address has been successfully deleted". | Nolak | Will do | High | Dev 1 | Bug 17
Address Book | First Name and Last name field accepts integers. First Name and Last name field should not accept integers and error messege will be shown under First Name and Last Name field. | Nolak | Will do | Medium | Dev 1 | Bug 18
Wishlist | In Wishlist,Canon EOS 5D and Apple Cinema 30" show their product display page when their Add to Cart logo is clicked. Canon EOS 5D and Apple Cinema 30" products should be added to Add to Cart list when Add to Cart logo is clicked in Wishlist. | Nolak | Will do | Medium | Dev 2 | Bug 19
Payment | Payment page favicon does not shows. Payment page favicon should be added to the page. | Nolak | Will do | Medium | Dev 2 | Bug 20
Product Returns | Account page is viewed when Product Returns's all the products View buttons are clicked. Should be able to view each product's details when each of their view button will be clicked. | Nolak | Will do | Medium | Dev 2 | Bug 21
Affiliate Account>My Affiliate Account | "Web site" field name must not have space in between web and site. The correct field name should be written as "Website" . | Nolak | Not an issue | Low | Dev 1 | Bug 22
Affiliate Account>My Affiliate Account | Company name field accepts spaces between company name characters. Company name field should not accept spaces between company name characters. | Nolak | Not an issue | Low | Dev 1 | Bug 23
Affiliate Account>My Affiliate Account | Website field accept domain address with hyphen. Website field should not accept domain address with hyphen. | Nolak | Will do | Medium | Dev 2 | Bug 24
Affiliate Account>My Affiliate Account | Website field accept domain address that has spaces between words or characters. Website field should not accept domain address with any kind of spaces between words or charcaters. | Nolak | Will do | Medium | Dev 1 | Bug 25
Affiliate Account>My Affiliate Account | Website field accept invalid format domain address . Website field should not accept invalid format domain address. | Nolak | Will do | Medium | Dev 2 | Bug 26
Affiliate Account>Payment Information | Tax ID field accepts letters and special characters. Tax ID field should not accept letters and special characters. | Nolak | Won't fix | Low | Dev 1 | Bug 27
Affiliate Account>Payment Information>Payment Method>Cheque | Cheque Payee Name field accepts integers and special character. Cheque Payee Name field should not accept integers and special characters except fullstop,hyphen and apostrophe. | Nolak | Future release | Low | Dev 2 | Bug 28
Affiliate Account>Payment Information>Payment Method>Bank Transfer | ABA/BSB number (Branch Number) field accepts letter and special characters. ABA/BSB number (Branch Number) field should not accept letter and special characters. | Nolak | Will do | Medium | Dev 2 | Bug 29
Affiliate Account>Payment Information>Payment Method>Bank Transfer | Bank Name field accepts integers and special characters. Bank Name field should not accept integers and special characters. | Nolak | Will do | Low | Dev 1 | Bug 30
Affiliate Account>Payment Information>Payment Method>Bank Transfer | SWIFT Code field accepts less than 8 digit number. SWIFT Code field should accept 8 to11digit numbers. | Nolak | Will do | Medium | Dev 1 | Bug 31
Affiliate Account>Payment Information>Payment Method>Bank Transfer | SWIFT Code field accepts more than 11 digit number. SWIFT Code field should accept 8 to11digit numbers. | Nolak | Will do | Medium | Dev 1 | Bug 32
Affiliate Account>Payment Information>Payment Method>Bank Transfer | SWIFT Code field accepts letters and special characters. SWIFT Code field should not accept letters and special characters. | Nolak | Will do | Medium | Dev 2 | Bug 33
Affiliate Account>Payment Information>Payment Method>Bank Transfer | Account name field accepts integers and special characters. Account name field should not accept integers and special characters except fullstop,hyphen and apostrophe. | Nolak | Future release | Low | Dev 2 | Bug 34
Gift Certificate>Purchase a Gift Certificate | Recipient's Name field accepts digits and special characters and form is submitted and Purchase a Gift Certificate page is shown. Recipient's Name field should not accepts digits and special characters except fullstop,hyphen and apostrophe and error message should be shown "Recipient's Name has invalid formats!" | Nolak | Will do | Medium | Dev 1 | Bug 35
Gift Certificate>Purchase a Gift Certificate | Your Name field accepts digits and special characters and form is submitted and Purchase a Gift Certificate page is shown. Your Name field should not accepts digits and special characters except fullstop,hyphen and apostrophe and error message should be shown "Recipient's Name has invalid formats!" | Nolak | Will do | Medium | Dev 2 | Bug 36
Gift Certificate>Purchase a Gift Certificate | Message field accepts letters with spaces between each characters and form is submitted and Purchase a Gift Certificate page is shown. . Message field should not aceept letters with spaces after each character. | Nolak | Will do | Medium | Dev 1 | Bug 37
Gift Certificate>Purchase a Gift Certificate | Message field accepts small letters after fullstop in a sentence and form is submitted and Purchase a Gift Certificate page is shown. . Message field should not accepts small letters after fullstop in a sentence. | Nolak | Will do | Low | Dev 2 | Bug 38
Gift Certificate>Purchase a Gift Certificate | Purchase a Gift Certificate form is submitted without checking the "I understand that gift certificates are non-refundable" checkbox. Purchase a Gift Certificate form should be submitted after checking the "I understand that gift certificates are non-refundable" checkbox. | Nolak | Will do | Medium | Dev 1 | Bug 39
Shopping Cart>Quantity | Clicking cross sign of all the gift vouchers quantity box from Quantity column does not remove the gift voucher from Shopping Cart. Gift Voucher should be removed when quantity box cross mark (Remove) will be clicked. | Nolak | Will do | Medium | Dev 2 | Bug 40
Shopping Cart>What would you like to do next?> Estimate Shipping and Taxes | Post code accepts special characters and letters and able to submit form. Post code should not accepts special characters and letters and form should not able to submit. | Nolak | Will do | Medium | Dev 2 | Bug 41
Contact Us>Contact Form | Your Name field accepts integers and special characters and contact form is submitted and Home page is viewed. Your Name field should not accept integers and special characters except fullstop,hyphen and apostrophe and contact form should not be submitted. | Nolak | Will do | Medium | Dev 1 | Bug 42
Contact Us>Contact Form | Enquiry field accepts values that has spaces after each characters and contact form is submitted and Home page is viewed. Enquiry field should not accepts values that has spaces after each characters and contact form should not be submitted. | Nolak | Will do | Medium | Dev 1 | Bug 43
Specials | Canon EOS 5D and Apple Cinema 30" show their product display page when their Add to Cart logo is clicked. Canon EOS 5D and Apple Cinema 30" products should be added to Add to Cart list when Add to Cart logo is clicked in Specials page. | Nolak | Duplicate | Medium | Dev 2 | Bug 44 | Duplicate bug
Product Compare | HP LP3065, Apple Cinema 30" and Canon EOS 5D product Add to Cart button takes to the product display page in product Compare page. HP LP3065, Apple Cinema 30" and Canon EOS 5D product should be added to Shopping Cart when Add to Cart button is clicked. | Nolak | Will do | Medium | Dev 2 | Bug 45
Product Compare | To visit Product Compare page by searching the product through search box user search the product and search result shows internal error-500. User should visit product Compare page by searching a product through search box. | Nolak | Duplicate | Low | Dev 2 | Bug 46 | Duplicate bug
Product Display | Canon EOS 5D Tab name is 'sdf' and it's 'Please Select' button does not show any selectable options.. Canon EOS 5D tab name should be 'Canon EOS 5D' and it's 'Please Select' button should show selectable options. . | Nolak | Will do | Medium | Dev 2 | Bug 47
Product Display | When all the products Qty field remains empty and 'Add to Cart' button is clicked success message is shown without adding the product to Shopping Cart and 'Please Select' button does not show any selectable options. Success message should not be shown. | Nolak | Will do | Medium | Dev 2 | Bug 48
Product Display>Reviews(0)>Write a review | Your Review field accepts spaces between each character in a sentence. Your Review field should not accept spaces between each character in a sentence. | Nolak | Future release | Low | Dev 1 | Bug 49
Product Display>Reviews(0)>Write a review | Your Review field accepts small letters to start a sentence. Your Review field should not accept small letters to start a sentence. | Nolak | Won't fix | Low | Dev 1 | Bug 50
Product Display>Reviews(0)>Write a review | Your Name field accepts integers and special characters. Your Name field should not accept integers and special characters except full stop,hyphen,Apostrophe s. | Nolak | Future release | Low | Dev 2 | Bug 51
Product Display>Reviews(0)>Write a review | Your name field accepts any randnom names. Your name field should accept only user's username. | Nolak | Will do | Medium | Dev 2 | Bug 52